## Sheet
RISK ID | RISK NAME | BASE_SEVERITY | BASE_LIKELIHOOD | MITIGATION | TARGET_DATE
R-001 | Adversarial Examples | High | High | Implement adversarial training and input validation; monitor for adversarial inputs. | 2025-12-31
R-002 | Model Stealing | High | Medium | Apply rate-limiting, watermarking, and access controls to model APIs; monitor for unusual querying patterns. | 2025-12-31
R-003 | Backdoor Attacks (Foundation) | High | Medium | Perform code and model audits, sign and verify model artifacts, and implement runtime monitoring for unexpected triggers. | 2025-12-31
R-004 | Membership Inference Attacks | Medium | Medium | Use differential privacy techniques and limit query results; audit model outputs for information leakage. | 2025-12-31
R-005 | Data Poisoning (Training Phase) | High | High | Sanitize and validate training data; employ anomaly detection and robust training techniques. | 2025-12-31
R-006 | Reprogramming Attacks | High | Low | Restrict model access and use formal verification to ensure models are used as intended. | 2025-12-31
R-007 | Foundation Model DoS | High | Medium | Implement rate limiting and scaling; detect and filter malicious queries. | 2025-12-31
R-008 | Data Poisoning (Data Ops) | High | High | Apply data sanitization, validation, and anomaly detection; implement robust data governance. | 2025-12-31
R-009 | Data Exfiltration | High | Medium | Encrypt data in transit and at rest; enforce strict access controls and monitoring. | 2025-12-31
R-010 | Data Infrastructure DoS | High | Medium | Implement redundancy, load balancing, and rate limiting to maintain availability. | 2025-12-31
R-011 | Data Tampering | High | Medium | Use integrity checks, cryptographic signatures, and secure channels for data storage and transmission. | 2025-12-31
R-012 | Compromised RAG Pipelines | Medium | Medium | Secure retrieval-augmented generation pipelines with code reviews, isolation, and monitoring. | 2025-12-31
R-013 | Compromised Framework Components | High | Medium | Vet and monitor third-party dependencies; use code signing and vulnerability scanning. | 2025-12-31
R-014 | Backdoor Attacks (Framework) | High | Medium | Conduct thorough code reviews and security testing of AI frameworks; enforce supply chain security. | 2025-12-31
R-015 | Input Validation Attacks | Medium | Medium | Implement strict input validation and sanitization across all APIs and user inputs. | 2025-12-31
R-016 | Supply Chain Attacks (Framework) | High | Medium | Use secure software supply chain practices, such as signed packages and SBOMs. | 2025-12-31
R-017 | Framework API DoS | Medium | Medium | Implement rate limiting and authentication for framework APIs; monitor for abuse. | 2025-12-31
R-018 | Framework Evasion | Medium | Low | Apply behavioural analytics and anomaly detection to detect evasion techniques. | 2025-12-31
R-019 | Compromised Container Images | High | High | Use signed and scanned container images; employ runtime protection. | 2025-12-31
R-020 | Orchestration Attacks | High | Medium | Secure orchestration platforms (e.g., Kubernetes) with RBAC, network policies, and regular patching. | 2025-12-31
R-021 | IaC Manipulation | High | Low | Perform code reviews on IaC scripts; use automated scanning and secrets management. | 2025-12-31
R-022 | Deployment DoS | High | Medium | Implement auto-scaling, redundancy, and DDoS protection for deployment infrastructure. | 2025-12-31
R-023 | Resource Hijacking | Medium | Medium | Monitor resource usage and implement quotas; detect and respond to unauthorized resource use. | 2025-12-31
R-024 | Lateral Movement | High | Medium | Use network segmentation, microsegmentation, and robust IAM to prevent lateral movement. | 2025-12-31
R-025 | Manipulation of Evaluation Metrics | Medium | Medium | Ensure integrity of evaluation datasets and metrics; perform cross-validation and monitoring. | 2025-12-31
R-026 | Compromised Observability Tools | High | Medium | Secure observability tools with code reviews, hardened configurations, and access controls. | 2025-12-31
R-027 | Evaluation Infrastructure DoS | High | Medium | Implement redundancy and scaling for evaluation infrastructure; use rate limiting. | 2025-12-31
R-028 | Evasion of Detection | Medium | Medium | Use behavioral analytics and continuous monitoring to detect evasive behavior. | 2025-12-31
R-029 | Data Leakage via Observability | High | Medium | Enforce strict access control and encryption on logs and monitoring data; redact sensitive information. | 2025-12-31
R-030 | Poisoning Observability Data | High | Medium | Validate and verify observability data; implement anomaly detection to identify poisoning attempts. | 2025-12-31
R-031 | Security Agent Data Poisoning | High | High | Sanitize training data for security agents; monitor for anomalies and use adversarial training. | 2025-12-31
R-032 | Evasion of Security AI Agents | High | High | Harden AI security agents with adversarial training and continuous learning; monitor for evasive attacks. | 2025-12-31
R-033 | Compromised Security AI Agents | High | Medium | Implement strong access control and monitoring; update and patch security agents regularly. | 2025-12-31
R-034 | Regulatory Non-Compliance (Security Agents) | Medium | Medium | Ensure AI security agents comply with privacy and regulatory requirements; conduct regular audits. | 2025-12-31
R-035 | Bias in Security AI Agents | Medium | Medium | Evaluate and mitigate bias in AI security agents; use fairness metrics and diverse training data. | 2025-12-31
R-036 | Lack of Explainability (Security Agents) | Medium | Medium | Implement explainable AI (XAI) techniques to make decisions of security agents transparent. | 2025-12-31
R-037 | Model Extraction of Security AI Agents | Medium | Medium | Use watermarking, query limitation, and monitoring to prevent model extraction. | 2025-12-31
R-038 | Compromised Agents | High | High | Vet agents before deployment; implement strong identity verification and continuous monitoring. | 2025-12-31
R-039 | Agent Impersonation | High | High | Use strong authentication and identity management to prevent impersonation. | 2025-12-31
R-040 | Agent Identity Attack | High | High | Protect identity credentials and use MFA; monitor for unauthorized access attempts. | 2025-12-31
R-041 | Agent Tool Misuse | Medium | Medium | Enforce usage policies and monitor tool usage; restrict tool access based on need. | 2025-12-31
R-042 | Agent Goal Manipulation | High | Medium | Validate goal inputs and maintain alignment monitoring; restrict changes to agent goals. | 2025-12-31
R-043 | Marketplace Manipulation | Medium | Medium | Implement review and validation processes for ratings and reviews; monitor for anomalies. | 2025-12-31
R-044 | Integration Risks | High | Medium | Use secure APIs and SDKs with authentication, authorization, and encryption; perform integration testing. | 2025-12-31
R-045 | Horizontal/Vertical Solution Vulnerabilities | Medium | Medium | Conduct security assessments of industry-specific AI solutions; apply patches and harden configurations. | 2025-12-31
R-046 | Repudiation (Agent Actions) | Medium | Low | Implement non-repudiation mechanisms such as logging, digital signatures, and audit trails. | 2025-12-31
R-047 | Compromised Agent Registry | High | Medium | Secure the agent registry with authentication, authorization, and integrity checks; monitor changes. | 2025-12-31
R-048 | Malicious Agent Discovery | High | Medium | Use reputation systems and vetting processes to identify and block malicious agents; update discovery algorithms. | 2025-12-31
R-049 | Agent Pricing Model Manipulation | Medium | Low | Secure pricing algorithms with validation and monitoring; audit transactions for anomalies. | 2025-12-31
R-050 | Inaccurate Agent Capability Description | Medium | Medium | Require standardized capability descriptions and verify claims through testing; maintain up-to-date catalogs. | 2025-12-31
R-051 | Supply Chain Attack (Cross-Layer) | High | High | Adopt supply chain risk management practices, including SBOMs, attestation and continuous monitoring. | 2025-12-31
R-052 | Privilege Escalation (Cross-Layer) | High | Medium | Implement least privilege policies and robust access controls across all layers. | 2025-12-31
R-053 | Data Leakage (Cross-Layer) | High | Medium | Protect data via encryption, access control, and secure communication across layers. | 2025-12-31
R-054 | Goal Misalignment Cascades | High | Low | Monitor agent behaviors and update goals to ensure alignment; implement safeguards to detect cascading effects. | 2025-12-31
R-055 | Communication Channel Attack | High | Medium | Secure communications between agents with encryption, authentication, and integrity verification. | 2025-12-31
R-056 | Prompt Injection / Jailbreaking | High | High | Implement robust input filtering, prompt validation, and context isolation to prevent injection attacks. | 2025-12-31
R-057 | Higher-Level Agent Compromise | High | Medium | Secure control channels; enforce strong authentication and access control between hierarchical agents. | 2025-12-31
R-058 | Sybil Attack / Agent Impersonation | High | Medium | Use identity proofing, reputation systems, and consensus mechanisms to prevent Sybil attacks. | 2025-12-31
R-059 | Manipulation of Human Feedback | Medium | Medium | Validate and audit human input and feedback; implement training processes to detect manipulation. | 2025-12-31
R-060 | Data Poisoning via Backdoor Injection | High | High | Use data sanitization and backdoor detection methods to identify and remove backdoor triggers. | 2025-12-31